PROJECTS IMPLEMENTATION STATUS IN THE WORKS DEPARTMENT DURING FY 2025/2026

- Releases as of end of September FY 2026/27

| S/No | Funding source | Category | Budget | Funds received | Balances |
| --- | --- | --- | --- | --- | --- |
| 1 | Uganda Road Fund | District | 155,720,344 | 146,013,602 | 9,706,742 |
|  |  | Sub counties | 108,421,392 | 108,421,392 | 0 |
|  |  | Busunju Town Council | 37,632,385 | 35,287,080 | 2,345,305 |
|  | Sub Total URF |  | 301,774,121 | 289,722,074 | 12,052,047 |
| 2 | Rehabilitation Grant (MoWT) | District | 1,000,000,000 | 1,000,000,000 | 0 |
| Grand Total |  |  | 1,301,774,121 | 1, 289,722,074 | 12,052,047 |

- Status of implementation of projects for FY 2025/26

| S/No | Project description | Length (km) | Budget | Amount spent | Completion status | Project launching/ data | Source of funding | Scope of works |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Mechanized routine maintenance Kambuzi-Wabiyinja-Kakindu | 7.9 | 148,905,000 | 123,099,800 | 100% complete | Date: 12/06/26 Road Management Committee members Nakiyingi Regina Ssemugenyi Mpiso Robert Kiyingi Edison Batte Charles Lutale Peter Mutyaba Resty Kabada Musawo | Maintenance grant | Included Mobilization and demobilization of equipment, bush clearing opening and shaping, and compaction, gravelling works, drainage works |
|  | Mechanized routine maintenance Kikonge-Kanyanya | 8 | 88,993,000 | 75,453,000 | 100% complete | Date: 7/04/26 Road Management Committee members Ssebufu John Ssenyondo Mike Namubiru Ruth Byakatonda Peter Kajabaga Lawrence Bogere Steven Lwere Matovu Faluk Nakitto Florence | Maintenance grant | Included Mobilization and demobilization of equipment, bush clearing opening and shaping, and compaction, filling and raising of Kizikibi swamp gravelling works, drainage works |
|  | Mechanized routine maintenance Kitongo-Maanyi | 12.2 | 94,568,600 | 94,568,600 | 100% complete | Date: Road Management Committee members Mujambi Chrizotom Kaweesi John Katdiita Maria Namayanja Olivia Ssebunya Moses Kyobe Posiano Matovu Joseph Kizito Nathan Kyerima David | Maintenance grant | Included Mobilization and demobilization of equipment, bush clearing opening and shaping, and compaction, gravelling works, drainage works |
|  | Mechanized routine maintenance Kalaalo-Kalangaalo | 14 | 173,977,400 | 173,977,400 | 100% complete | Date: 30/09/25 Road Management Committee members Ssekyewa Charles Lugemwa Joseph Mukamazera Veronica Bira Gertrude Ssekitoleko Abud Ssempewo Edward Mwebe Robert Nsubuga Fred Munyegenye Paul | Maintenance grant | Included Mobilization and demobilization of equipment, bush clearing opening and shaping, and compaction, filling and raising of Kalaalo and Ngonza swamps, gravelling works, drainage works |
|  | Mechanized routine maintenance Kasanda boarder-Kyamusisi-Magala boarder | 9.8 | 72,837,700 | 62,137,700 | 100% complete | Date: 20/05/26 Road Management Committee members Menge Deo Kibuga Elusama Ssekutte Moses Kiberu Geofrey Lule John Dezirata Mulemu Balanya Tadeo Ssempira Swaibu Kamya Peter Wasswa Moses | Maintenance grant | Included Mobilization and demobilization of equipment, bush clearing opening and shaping, and compaction, gravelling works, drainage works |
|  | Mechanized routine maintenance Kigogolo swamp | 1.8 | 62,909,000 | 62,909,000 | 100% complete | Date: 16/3/26 Road Management Committee members Ssekanjako Ronald Mwajje Samuel Kyanbadde Charles Nakamatte Annet Matovu Abbey Nantume Ruth Nabulya Ssebuliba Sudaisi Bbaale Ashiraf Kawoya Abubakar | Maintenance grant | Included Mobilization and demobilization of equipment, bush clearing opening of the swamp and shaping, and compaction, and drainage works |
|  | Mechanized routine maintenance Kasenyi-Mpirigwa | 10.5 | 62,769,200 | 59,139,200 | 80% | Date: 3/7/26 Road Management Committee members | Maintenance grant | Included Mobilization and demobilization of equipment, bush clearing opening and shaping, and compaction, gravelling works, drainage works |
|  | Mechanized routine maintenance Matte and Fululu swamp | 0.7 | 38,500,000 | 35,401,800 | 100% complete | Date: Road Management Committee members Lwebuga Emma Mulindwa Robert Kalyango Fedrick Bussa Luke Muwanga Dirisa Kwagala Betty Nakanwagi Christine Bukenya Hammed Nyanzi Fedirck | Maintenance grant | Included Mobilization and demobilization of equipment, bush clearing opening and shaping, and compaction, filling of both Fululu and Matte swamps and drainage works |
|  | Mechanized routine maintenance Kyakosi-Katiti-Katungulu-Nakiragala-Budimbo-Kikunyu | 19.1 | 135,367,200 | 135,367,200 | 100% complete | Date: 11/10/25 Road Management Committee members Yisiko Twaha Kiyimba Faluku Tudeka Muhamed Kalimu Lubwama Buying Patrick Dala Numan Epafula Lukwago Sseruyage Abdul Kalim Swalid Bahizi Ssefubwe Vicent | Maintenance grant | Included Mobilization and demobilization of equipment, bush clearing opening and shaping, and compaction, gravelling works, drainage works |
|  | Emergencies | 5 | 21,172,900 | 21,172,900 | 100% of the funds used |  | Maintenance grant | Works so far done include Ddundu-Namasenene, emergency works along Namudaali swamp, emergency works for roads during the president’s visit and extra culverts along Bulera-Kiryokya, extra culverts along Fululu and Matte swamp. |
|  | Administrative Costs |  |  |  |  |  |  |  |
|  | Mechanical Imprest |  | 100,000,000 | 100,000,000 | Q1, Q2 and Q3 expenditures on repairs for the wheel loader, roller and serviced grader |  | Maintenance grant | Repaired wheel loader, roller and serviced grader |
|  | Sub Total Rehabilitation grant | 88.7 km | 1,000,000,000 | 1,000,000,000 |  |  |  |  |
|  | Uganda Road Fund |  |  |  |  |  |  |  |
|  | Mechanized routine maintenance Nakwaya-Kabulamuliro | 7.8km | 79,913,000 | 72,975,880 | 80% complete | Date: 9/07/26 Road Management Committee members Ssekitto Geofrey Buyondo Aloyzious Kasenere Henry Kaggudde Joseph Twaha Nakabugo Annet Ssebagala Henry Nanteza Mary Mutebi Christopher | URF | Included Mobilization and demobilization of equipment, bush clearing opening and shaping, and compaction, gravelling works, drainage works |
|  | Mechanized routine maintenance of Ndoge-Nakaziba | 4.3km | 15,963,695 | 15,363,696 | 100% complete | Date: | URF | Included Mobilization and demobilization of equipment, bush clearing opening and shaping of the road section. |
|  | Manual routine maintenance | 282.2 km | 68,799,929 | 47,655,000 | Works for the months of November and April. |  | URF | Gangs were deployed and works done for the FY 25/26 and paid the workers for the months of November and April. |
|  | Maintenance of Subcounty roads | 29 km | 108,421,392 | 108,421,392 | Funds transferred as received |  | URF | Funds transferred as received |
|  | Transfers to Busunju TC | 3.8 km | 37,632,385 | 35,287,080 | Transferred Q1, Q2 and Q3 road maintenance funds to Busunju TC |  | URF | Funds transferred works not yet started |
|  | Administrative costs |  |  |  |  |  |  |  |
|  | Administrative costs |  | 2,000,000 | 2,000,000 | Funds spent as received |  | URF | Funds spent as received |
|  | Allowances |  | 1,550,870 | 1,550,870 | Paid allowances to staff in works department for Q1, Q2, Q3 and Q4. |  | URF | Paid allowances to staff in works department for Q1, Q2, Q3 and Q4. |
|  | Departmental Fuel |  | 3,456,545 | 3,456,545 | Funds spent as received |  | URF | Funds spent as received |
|  | Sub Total URF |  | 301,774,121 | 289,722,074 |  |  |  |  |

Complied by

Katende Jack

District Engineer

PHOTOS OF THE WORKS DONE

|  | Kyamusisi |
| --- | --- |
| Fululu and Matte before rehabilitation | Fululu and Matte during rehabilitation |
| Kikonge-kanyanya road before rehabilitation | Kikonge-kanyanya road during rehabilitation |
|  | Kalaalo swamp after during opening |
| Kigogolo Swamp before rehabilitation | Kigogolo Swamp after rehabilitation |
| Works along Nakwaya-kabulamuliro | Completed section along Nakwaya-Kabulamuliro |
| Section of Kyakosi-Nakilagala-Bidimbo-Kikunyu road before rehabilitation. | Section of Kyakosi-Nakilagala-Bidimbo-Kikunyu road during rehabilitaion. |
| Section of Kambuzi-Wabiyinja-Kakindu road durig rehabilitation (opening of swamp) | Section of Kambuzi-Wabiyinja-Kakindu road durig rehabilitation |